## Project Summary
SCOTTSDALE PROMENADE CENTER
Project No: PR456 ¦ Commercial Build-to-Sell ¦ Scottsdale, AZ
Description | A 168,000 SF ground-up mixed-use retail and office development in north Scottsdale, anchored by two junior box retail tenants and a 4-story Class A office building, with structured parking and a central pedestrian plaza connecting both uses.
Project Type | Commercial (Retail + Office)
Creator Role | General Contractor
Address | 8350 E Raintree Dr, Scottsdale, AZ 85260
County | Maricopa
Total Saleable Area | 168,000 sq.ft
Land Area | 9.2 acres
Status | Under Construction
Schedule | 2025-09-15 to 2026-11-30
Working Days | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday
Total Contract Value | 62732000

## Cost Divisions (SOV)
SCHEDULE OF VALUES — CSI DIVISION COST CONTROL
Budget vs. Actual vs. Committed, by CSI MasterFormat division ¦ Construction cost only (excl. land/soft cost)
Div # | Division Name | Contract Value | Actual to Date | Committed | Total Exposure | % Complete | Variance | Status
01 | General Conditions & Fee | 1568200 | 1393300 | 193600 | 1586900 | 87.8% | -18700 | On Track
02 | Sitework | 2156800 | 2064000 | 138800 | 2202800 | 93.7% | -46000 | On Track
03 | Concrete | 4704600 | 4655800 | 426900 | 5082700 | 91.6% | -378100 | Watch
04 | Masonry and Facade Treatment | 2745400 | 2208300 | 452300 | 2660600 | 83% | 84800 | On Track
05 | Metals / Structural Steel | 4116000 | 3328900 | 696400 | 4025300 | 82.7% | 90700 | On Track
06 | Wood, Plastics and Composites | 782000 | 376900 | 420000 | 796900 | 47.3% | -14900 | On Track
07 | Thermal and Moisture Protection | 2156800 | 1184400 | 823100 | 2007500 | 59% | 149300 | On Track
08 | Doors, Windows and Glazing | 3136400 | 1844400 | 1912000 | 3756400 | 49.1% | -620000 | Over Budget
09 | Finishes | 3527400 | 2123500 | 1108600 | 3232100 | 65.7% | 295300 | On Track
10 | Specialties | 588600 | 169400 | 408800 | 578200 | 29.3% | 10400 | On Track
14 | Conveying Systems (Elevators/Escalators) | 1370600 | 1084000 | 320100 | 1404100 | 77.2% | -33500 | On Track
21 | Fire Suppression | 979600 | 368500 | 606400 | 974900 | 37.8% | 4700 | On Track
22 | Plumbing | 2350200 | 389200 | 1998300 | 2387500 | 16.3% | -37300 | On Track
23 | HVAC / Mechanical | 4507000 | 1092800 | 4037900 | 5130700 | 21.3% | -623700 | Over Budget
26 | Electrical | 3725000 | 694600 | 3297600 | 3992200 | 17.4% | -267200 | Watch
31 | Earthwork | 1177200 | 1084500 | 75400 | 1159900 | 93.5% | 17300 | On Track
32 | Exterior Improvements / Parking & Landscaping | 1568200 | 455400 | 1148000 | 1603400 | 28.4% | -35200 | On Track
TOTAL |  | 41160000 | 24517900 | 18064200 | 42582100 |  | -1422100 | -3.455%

## Permits
PERMITS & APPROVALS
Status as of June 20, 2026
Permit Type | Issuing Authority | Budgeted Cost | Status | Target Date | Actual Date | Blocking | Notes
Grading Permit | City of Scottsdale - Development Services | 18500 | Approved | 2025-10-01 | 2025-09-28 | Yes | Approved ahead of schedule.
Building Permit | City of Scottsdale - Building Safety Division | 142000 | Approved | 2025-12-01 | 2025-12-19 | Yes | Plan revision cycle added 3 weeks.
Fire Department Approval | Scottsdale Fire Department | 9500 | Under Review | 2026-05-20 | — | Yes | Sprinkler layout resubmittal requested.
Electrical Permit | City of Scottsdale - Building Safety Division | 22000 | Revisions Requested | 2026-04-30 | — | No | Service entrance size revision requested by reviewer.
Mechanical Hvac Permit | City of Scottsdale - Building Safety Division | 19500 | Submitted | 2026-06-10 | — | No | Equipment cut sheets pending from mech sub.
Water Connection | City of Scottsdale Water Resources | 31000 | Submitted | 2026-05-25 | — | Yes | Tap fee invoice pending; inspection not yet scheduled.
Sign Permit | City of Scottsdale - Development Services | 4200 | Not Started | 2026-08-01 | — | No | Monument sign package to be submitted post-tenant lease-up.
Certificate Of Occupancy | City of Scottsdale - Building Safety Division | 6500 | Not Started | 2026-11-15 | — | Yes | Final inspection requires all trades substantially complete.
Elevator Permit | Arizona Department of Building & Fire Safety | 8200 | Not Started | 2026-09-15 | — | No | Filed once elevator equipment is on site.
⚠ 2 permit(s) at risk (blocking + overdue):
• Fire Department Approval — 31 days overdue
• Water Connection — 26 days overdue

## Change Orders
CHANGE ORDER TRACKING
Summary of cost and schedule changes to date
CR # | Description | Status | Cost Impact | Schedule Impact | Due Date | Requested By | Created Date
CR-001 | Curtain wall glazing upgrade per ownership request (impact glass spec change) | Signed | 287500 | 0 days | 2026-02-15 | Ownership Rep - Promenade Holdings LLC | 2026-01-20
CR-002 | Revised electrical service entrance size per utility coordination | Approval Pending | 64200 | 7 days | 2026-06-30 | Matt Hefner, Project Manager | 2026-05-20
CR-003 | Unforeseen rock excavation in northeast parking area, geotechnical addendum | Submitted | 118900 | 5 days | 2026-07-10 | Matt Hefner, Project Manager | 2026-06-12
CR-004 | Tenant-driven HVAC zoning revision for anchor retail suite | Draft | 41000 | 0 days | — | Leasing Coordinator | 2026-06-18
Pending Cost Exposure: |  |  | 183100
Approved Cost Impact: |  |  | 287500

## Schedule Health
SCHEDULE HEALTH — LATE TASKS
6 tracked tasks, 5 late, max 42 days late
Task | Div # | Planned Start | Planned End | Actual Start | Actual End | Days Late
Main electrical switchgear delivery and set | 26 | 2026-05-01 | 2026-05-10 | — | — | 42
Rooftop HVAC equipment set (RTUs) | 23 | 2026-04-20 | 2026-05-15 | — | — | 31
Furnish and install curtain wall glazing system | 08 | 2026-04-06 | 2026-05-04 | 2026-04-29 | — | 23
Elevator equipment delivery | 14 | 2026-06-01 | 2026-06-15 | — | — | 18
Interior framing - Building B tenant spaces | 09 | 2026-05-10 | 2026-06-01 | 2026-05-22 | — | 12
Site concrete - parking structure deck pour | 03 | 2026-01-10 | 2026-01-25 | 2026-01-10 | 2026-01-25 | 0

## Compliance Center
VENDOR COMPLIANCE CENTER
Missing or expired vendor documentation
Vendor | Document Type | Status | Expiration Date
Sonoran Steel Erectors LLC | Certificate Of Insurance | Approved | 2026-12-01
Sonoran Steel Erectors LLC | License | Approved | 2027-03-15
Desert Mechanical Systems Inc | Certificate Of Insurance | Expired | 2026-04-30
Desert Mechanical Systems Inc | Safety | Missing | —
Valley Electrical Contractors | W9 | Missing | —
Valley Electrical Contractors | License | Approved | 2026-08-20
Apex Glazing & Curtain Wall | Certificate Of Insurance | Approved | 2026-07-10
Apex Glazing & Curtain Wall | Safety | Missing | —
Cactus Concrete & Excavation | Certificate Of Insurance | Approved | 2026-09-01
Cactus Concrete & Excavation | License | Missing | —
Cactus Concrete & Excavation | Safety | Missing | —

## Financials & ROI
REALIZED CASH POSITION & PROJECT ROI
Cash basis (Financial Progress) and underwritten return summary (forward-sale exit)
REALIZED CASH POSITION (Cash Basis)
Period | 2026-01-01 to 2026-06-20
Received from Owner | 28400000 | Construction loan + equity draws received
Paid to Subcontractors | -22180000
Other Expenses (GC overhead, permits, insurance) | -1640000
Net Realized Cash | 4580000
Retainage Held (from Subcontractors) | 1109000
Retainage Receivable (held by Owner) | 1420000
PROJECT ROI SUMMARY (Underwritten — Forward Sale Exit)
Total Project Cost (Land + Construction + Soft Cost + Contingency) | 62732000
Equity Invested (40%) | 25093000
Debt Drawn (60%) | 37639000
Interest Rate (Annual) | 8.25%
Construction Duration (months) | 20
Interest During Construction (estimated) | 2846000
Stabilized NOI (post lease-up) | 4950000
Exit Cap Rate (Scottsdale Class A, 2026E) | 6.75%
Exit Value (Stabilized NOI / Exit Cap Rate) | 73333333.3333
Selling Costs (2.5% of Exit Value) | 1833333.3333
Net Sale Proceeds (Exit Value − Selling Costs − Debt Payoff) | 33861000
Net Profit to Equity | 5922000
ROI (Net Profit ÷ Equity Invested) | 23.6%
MOIC (Net Sale Proceeds ÷ Equity Invested) | 1.3494